## Instructions
Instructions | Enter your team name as specified in the cell below. When doing cross-team acceptance testing, enter the name for the testing group. Fill-in the Test Plan worksheet with all the remaining User Stories in your Product Backlog. Since Product acceptance is from the perspective of the end-user, only add User Stories that pertain to the Owner or Buyer and do not include User Stories specifically for the REST API service (e.g. AS a developer...). As your user stories are refined, add the acceptance criteria for each user story. Use a separate worksheet to provide any specific test case data that the tester needs to use. As tests are performed in each sprint, indicate Pass/Fail. Note that there are separate columns for each sprint. The tester should add initials and a date in the comments column. If the test failed, the tester is required to add additional information about the failure. The status cell will color code based on the test results. The comments cell will color code when a test result exists but no information is entered. Save this test plan with a name formatted as "term-swen-261-sec-letter name", e.g. 2171-swen-261-10-a Speedy Racers.xslx. Submit this file per the instructions specified for the sprint submissions and cross-team testing.
Team Name | team-project-2225-swen-261-06-c-cowrelatedpun/
Testing Team Name | Team 2 Sinister Koalas

## Test Plan
User Story | Acceptance Criterion | Sprint 2 | Tester initials; date; comments (required if test failed)
As a developer I want there to be a file of user information so that I can properly create and maintain users for the estore. | Given a user id does not exist in the file when the controller is told to make a new user with the user ID then the controller creates the new user | Pass | JW; 3/19/2023; New user created with curl commands | Pass | JW; 4/6/2023
| Given a user ID exists with the file when the controller is told to delete the specific user ID then the controller deletes the specific user ID from the file | Pass | JW; 3/19/2023; User is deleted w/ curl if exists | Pass | JW; 4/6/2023
| given a user ID exists in the file when the controller is told to make a new user with that ID then the controller throws an UserAlreadyExists error | Pass | JW; 3/19/2023; New user is not created w/ curl if conflict exists | Pass | JW; 4/6/2023
| Given a user does not exist within the file when the controller is told to delete the specific user ID then the controller throws a UserDoesNotExist error | Pass | JW; 3/19/2023; Error is thrown when deleting nonexistent user w/ curl | Pass | JW; 4/6/2023
| Given a username doesn't exist within the file when the controller is asked to verify a user combo then the controller will refute the user credentials | Pass | JW; 3/19/2023; Tested this with getUser as thats what user.service.ts uses, and it errors w/ nonexistent users | Pass | JW; 4/6/2023
| Given a username does not exists within the file when the controller is asked to verify a user then the controller will acknowledge and verify the user credentials | Pass | JW; 3/19/2023; Test w/ getUser, successfully returns credentials if user exists | Pass | JW; 4/6/2023
As an administrator I want to be authenticated with administrative capabilities so that I can manage the e-store | GIVEN I'm an admin WHEN I enter my username and password THEN I log into my account | Pass | AC; 3/20/2023; Had to add the login for the admin, but now passes. | Pass | JW; 4/5/2023
| GIVEN I'm an admin WHEN I log into my account THEN I should be able to make changes to the inventory | Pass | AC; 3/20/2023; | Pass | JW; 4/5/2023
| GIVEN I'm an admin WHEN I log into my account THEN I should not have a shopping cart | Pass | AC; 3/20/2023 | Pass | JW; 4/5/2023
As a customer I want to be authenticated so that I can access my account and use the e-store in my own session | GIVEN I am a customer, when I log in using my username, I want to be logged into my account | Pass | JW; 3/20/2023 | Pass | JW; 4/5/2023
| GIVEN I am a customer, when I add things to my shopping cart, I want to be able to come back later and still have items in my shopping cart. | Pass | JW; 3/20/2023 | Pass | JW; 4/5/2023
| GIVEN I am a customer, when I want to create an account, I want to be able to register for one and be able to log back into it. | Pass | JW; 3/20/2023 | Pass | JW; 4/5/2023
As a customer, I want to be able to see product details, so that I can make an informed purchased. | Given there is a product image, when I click on the image, I will see the details of the product. | Pass | BM; 3/20/2023; counting homepage badges as images | Pass | JW; 4/5/2023
| Given there is a product name, when I click on the name, I will see the details of the product. | Pass | BM; 3/20/2023 | Pass | JW; 4/5/2023
| Given the product does not exist, when I visit that product page, a 404 Error will occur. | Pass | BM; 3/20/2023 | Fail | JW; 4/6/2023
As a user, I want to see the landing page when I enter the site so that the site is user friendly. | GIVEN the website is online WHEN I go directly to the websites URL THEN I arrive at the e-stores landing page | Pass | BM; 3/20/2023; default route fixed, redirects to landing page | Pass | JW; 4/5/2023
As a customer, I want to navigate to the checkout page to be able to buy my items. | Given I am a customer, when I click the checkout button, my shopping cart empties and I am able to buy my product. | Fail | JW; 3/21/2023; not implemented for this sprint | Pass | JW; 4/5/2023
| Given I am a customer, when I don't have any products in my cart, the checkout button is greyed out. | Fail | JW; 3/21/2023; not implemented for this sprint | Fail | JW; 4/5/2023; button doesn't show up
| Given I am an admin, I should not have access to the checkout. | Fail | JW; 3/21/2023; not implemented for this sprint | Pass | JW; 4/5/2023
As a customer, I want to be able to view a catalog of products so that I may see the products available for purchase. | Given some product exists, when I do not filter the results, that product will show up in the catalog list. | Pass | JW; 3/19/2023; all products show up in list when not filtered | Pass | JW; 4/5/2023
| Given some product exists with certain criteria, when I filter the results with that criteria, this product will show up in the catalog list. | Pass | JW; 3/19/2023; product is filtered successfully when input is entered into field | Pass | JW; 4/5/2023
| Given some product does not exist with certain criteria when I filter the results with that criteria, these products will not show up in the catalog list. | Pass | JW; 3/19/2023; products that do not meet criteria dont show up when input is entered into field | Pass | JW; 4/5/2023
As a customer, I want to be able to sign up for an account that I can log back into at a later date. | Given I want to create an account, when I designate a username for myself, then I will be given a customer account with that username | Pass | JW; 3/19/2023; account created successfully with name | Pass | JW; 4/5/2023
| Given I am logged in, I will not be able to see the create account page. | Pass | JW; 3/20/2023; Redirects to home page if logged in | Pass | JW; 4/5/2023
| Given I try to create an account with a username already in use, then I will receive an error and be asked to try another username | Pass | JW; 3/19/2023; Displays proper error message | Pass | JW; 4/6/2023
As a customer, I want there to be a navigation bar so that I can easily navigate the website. | Given there is a home icon, when I click on it, the site navigates to the landing page. | Fail | JW; 3/21/2023; not implemented for this sprint | Pass | JW; 4/5/2023
| Given there is a cart icon, when I click on it, my shopping cart appears. | Fail | JW; 3/21/2023; not implemented for this sprint | Pass | JW; 4/5/2023
| Given there is an account icon, when I click on it, I am shown my account details. | Fail | JW; 3/21/2023; not implemented for this sprint | Pass | JW; 4/5/2023
| Given there is a catalog icon, when I click on it, I am shown the catalog. | Fail | JW; 3/21/2023; not implemented for this sprint | Pass | JW; 4/5/2023
As a Administrator I want to manage the products in my inventory so that I can add, alter, and remove products for my customers to purchase | Given I am an admin when I open my dashboard then I can see my full inventory | Pass | AC; 3/20/23; when there is no inventory, list is empty, once I begin to create products they show up in the list | Pass | JW; 4/5/2023
| Given I am an admin when I add a item to my dashboard, it will be added to my inventory | Pass | AC; 3/20/23; Able to add products using the dashboard and they show up in inventory | Pass | JW; 4/5/2023
| Given I am an admin, when I alter a value in my inventory, it will be reflected in my stored inventory | Pass | AC; 3/20/23; Proucts are updated in inventory when changed on dashboard | Pass | JW; 4/5/2023
| Given I am an admin, when I click a button, then I will be able to remove the item from my inventory. | Pass | AC; 3/20/23; Removed items no longer appear in inventory | Pass | JW; 4/5/2023
As a customer, I want to be able to add products to my shopping cart so that I can proceed to checkout. | Given an item exists, when I try to add it to my shopping cart, a copy of that product is added to my shopping cart and I receive a 200 OK. | Pass | JW; 3/20/23; Items may be added via shopping cart page | Pass | AC 4/4/23 Items, weight, and prices are correctly added to cart
| Given an item doesn't exist, when I try to add it to my shopping cart, it does not add and I receive a 404 ERROR. | Pass | JW; 3/20/23; Attempting to add via backend results in 404 | Pass | AC 4/4/23 When I try to add inventory that does not exist than a warning comes up and nothing is added
| Given an item exists, when I try to remove it from my shopping cart, a copy of that product is removed from my shopping cart and I receive a 200 OK. | Pass | JW; 3/20/23; Removing works from shopping cart page | Pass | AC 4/4/23 Items are removed correctly from cart
| Given an item doesn't exist, when I try to remove it from my shopping cart, it does not remove and I receive a 404 ERROR. | Pass | JW; 3/20/23; Attempting to remove nonexistent item results in 404 in backend | Pass | AC 4/4/23 if there is nothing in the cart than the remove option is not available
As a customer I want to be able to checkout with my shopping cart so that I can purchase my items | Given I have items in my shopping cart that are in stock when I checkout, then I purchase the items, and the inventory is updated and I get a 200 OK | Fail | JW; 3/21/2023; not implemented for this sprint | Pass | AC 4/4/23 Changes to inventory now happen when items are added to cart, but the other information is updated and works
| Given I have no items in my shopping cart when I checkout I get a 400 BAD REQUEST. | Fail | JW; 3/21/2023; not implemented for this sprint | Pass | AC 4/4/23 No ability to checkout if there is nothing in the cart, handled by front and back end
| Given I have items in my shopping cart that are not in stock when I check out, then I receive a 409 CONFLICT. | Fail | JW; 3/21/2023; not implemented for this sprint | Pass | AC 4/4/23 Now that inventory is updated when items are added to cart, this is no longer an issue
As a User I want to be able to login and stay logged in so that I don’t have to keep logging in when I navigate to each page | Given I am a user, when I am not logged in, then I should be sent to the home page | Pass | JW: 3/20/23 : redirected to home page from main url when not logged in | Pass | JW; 4/5/2023; redirected from pages where appropriate
| Given I am logged in when I naviagate between pages, then I should stay logged in | Pass | JW: 3/20/23; login is saved when switching pages | Pass | JW; 4/5/2023
| Given I am logged in as a customer, when I attempt to naviagate to admin only pages, then I should be redirected back to the landing page | Pass | JW: 3/20/23; redirects if customer on admin only page | Pass | JW; 4/5/2023
| Given I am logged in as a admin, when I attempt to navigate to customer only pages, then I should be redirected back to the landing page | Pass | JW: 3/20/23; redirects if admin on customer only page | Pass | JW; 4/5/2023
As a Developer I want more code coverage so that my updates are more robust | GIVEN I run a code coverage report WHEN all unit tests pass THEN I should reach at least 90% average code coverage on the backend API | Pass | JW: 3/21/23; passes w/ 93% | Pass | BB 4/5/23
As an Customer, I want to view product images, so that I know what the product looks like. | Given a product has an image when I go to the product page I can see the image for the product |  |  | Pass | BB 4/5/23
| Given there are some products in the inventory, when I visit the catalog, I can see the images of the products |  |  | Pass | JW; 4/6/2023
| Given there are some products in the inventory, when I visit the home page, I can see the images of the featured products |  |  | Pass | JW; 4/6/2023
As a developer I want to store customer credit card information in the customer class so that I can access each customer’s credit cards for ease of use | Given a customer has an account, when they add a credit card to their account, then it should be stored for future use |  |  | Pass | BB 4/4/23
| Given a customer is trying to checkout their items, when they check out then they should have access to up to three of their previously used cards |  |  | Pass | JW; 4/6/2023
As a user I want to be able to login using my password so that my account is more secure | Given my account has a password, when I login to my account using the password then I am logged into my account |  |  | Pass | BB 4/5/23
As a user I want to have a password associated with my user so that I can have a more secure account | Given I am a new user, when I am creating my account, I will provide a password for my account. |  |  | Pass | BB 4/5/24
As a user I want there to be an account page so that I can edit my credit cards and password | Given I am logged in When I visit the account page I am presented with the credit card and password components |  |  | Pass | BB 4/5/25
| Given I am not logged in When I visit the account page then I am redirected to the login page |  |  | Pass | BB 4/5/26
As a user I want to be able to reset my password so that when I forget my password I can regain access to my account. | Given I want to change my password, when I reset my password, my password will change |  |  | Pass | BB 4/5/23
As a customer, I want the website to be aesthetically pleasing so I will enjoy using the site more. | Given I am a customer viewing the site then the site should have a uniform design |  |  | Pass | AC 4/4/23 Looks great. All site is uniform, requires fixes on individual css templates for cosmetic purposes
As a customer I want to be able to add my cards to my account and choose which to use at checkout so that I can make purchases with my credit card | GIVEN I am logged in WHEN I visit the account page THEN I am able to add and remove credit cards to my account |  |  | Pass | AC 4/5/23
| GIVEN I have credit cards saved on my account WHEN I try to checkout THEN I am able to choose which credit card to use when I checkout |  |  | Pass | AC 4/5/23
As an owner I want my product pages to be user friendly so people will buy more product | Given I am a customer when I view the product page then it should look appealing |  |  | Pass | AC 4/5/23 product details look good
As a user, I want the homepage to be stylish, so that I am invited to keep shopping. | Given I am a customer, when I look at the home page, then I should see a well organized assortment of featured products |  |  | Pass | AC 4/5/23 new base-template background color looks good
As a owner I want a nice looking catalog so that it makes people want to use my store | Given I am a customer when I look at the catalog then I am provided an easy to use and nice looking catalog |  |  | Pass | AC 4/5/23
As a user, I want the new user to look nice, so that I enjoy looking at the website. | Given I'm a user, when I access the new user page, it will look consistently styled with the rest of the website. |  |  | Pass | JW; 4/6/2023
As a user, I want the login page to look nice, so that I enjoy looking at the website. | Given I'm a user, when I access the login page, it will look consistently styled with the rest of the website. |  |  | Pass | JW; 4/6/2023
As a developer, I want my design documentation to be updated, so that I have the correct information. | Given I am a developer, I want to view the documentation so I understand the project. |  |  | Pass | BB: 4/6/2023
As a customer, I want the cart page to look nice so I can easily navigate it | Given I am a user, I want my shopping cart to look nice, so that i want to continue shopping |  |  | Pass | JW; 4/6/2023
As a admin, I want my dashboard to have a uniform appearance, so that I can easily move edit the inventory. | Given I am an admin, when I access the dashboard, then it will have a uniform appearance |  |  | Pass | JW; 4/6/2023
As a user I want to have a nice looking account page so that I will want to use it. | Given I have an account, when I go to my account page, my page will be easy to use and interact with |  |  | Pass | JW; 4/6/2023
As a user, I want the checkout page to look nice, so that I enjoy looking at the website. | Given I am a customer, when I access the checkout page, then it will have a uniform appearance |  |  | Pass | JW; 4/6/2023

## Test Plan Activity
User Story | Acceptance Criterion | Sprint 2 | Tester initials; date; comments (required if test failed) | Sprint 3 | Tester initials; date; comments (required if test failed) | Sprint 4 | Tester initials; date; comments (required if test failed)
As a developer I want there to be a file of user information so that I can properly create and maintain users for the estore. | Given a user id does not exist in the file when the controller is told to make a new user with the user ID then the controller creates the new user | Pass | JW; 3/19/2023; New user created with curl commands
| Given a user ID exists with the file when the controller is told to delete the specific user ID then the controller deletes the specific user ID from the file | Pass | JW; 3/19/2023; User is deleted w/ curl if exists
| given a user ID exists in the file when the controller is told to make a new user with that ID then the controller throws an UserAlreadyExists error | Pass | JW; 3/19/2023; New user is not created w/ curl if conflict exists
| Given a user does not exist within the file when the controller is told to delete the specific user ID then the controller throws a UserDoesNotExist error | Pass | JW; 3/19/2023; Error is thrown when deleting nonexistent user w/ curl
| Given a username doesn't exist within the file when the controller is asked to verify a user combo then the controller will refute the user credentials | Pass | JW; 3/19/2023; Tested this with getUser as thats what user.service.ts uses, and it errors w/ nonexistent users
| Given a username does not exists within the file when the controller is asked to verify a user then the controller will acknowledge and verify the user credentials | Pass | JW; 3/19/2023; Test w/ getUser, successfully returns credentials if user exists
As an administrator I want to be authenticated with administrative capabilities so that I can manage the e-store | GIVEN I'm an admin WHEN I enter my username and password THEN I log into my account | Pass | AC; 3/20/2023; Had to add the login for the admin, but now passes. |  |  | Pass | ax lc 4/4;.
| GIVEN I'm an admin WHEN I log into my account THEN I should be able to make changes to the inventory | Pass | AC; 3/20/2023; |  |  | Fail | ax lc 4/4; it updated with the wrong values.
| GIVEN I'm an admin WHEN I log into my account THEN I should not have a shopping cart | Pass | AC; 3/20/2023 |  |  | Pass | ax lc 4/4;
As a customer I want to be authenticated so that I can access my account and use the e-store in my own session | GIVEN I am a customer, when I log in using my username, I want to be logged into my account | Pass | JW; 3/20/2023 |  |  | Pass | ax lc 4/4;
| GIVEN I am a customer, when I add things to my shopping cart, I want to be able to come back later and still have items in my shopping cart. | Pass | JW; 3/20/2023 |  |  | Pass | ax lc 4/4;
| GIVEN I am a customer, when I want to create an account, I want to be able to register for one and be able to log back into it. | Pass | JW; 3/20/2023 |  |  | Pass | make it so you dont have to refresh the page
As a customer, I want to be able to see product details, so that I can make an informed purchased. | Given there is a product image, when I click on the image, I will see the details of the product. | Pass | BM; 3/20/2023; counting homepage badges as images |  |  | Fail | ax lc 4/4; there is no image
| Given there is a product name, when I click on the name, I will see the details of the product. | Pass | BM; 3/20/2023 |  |  | Pass | ax lc 4/4;
| Given the product does not exist, when I visit that product page, a 404 Error will occur. | Pass | BM; 3/20/2023 |  |  | Pass | ax lc 4/4;
As a user, I want to see the landing page when I enter the site so that the site is user friendly. | GIVEN the website is online WHEN I go directly to the websites URL THEN I arrive at the e-stores landing page | Pass | BM; 3/20/2023; default route fixed, redirects to landing page |  |  | Pass | ax lc 4/4;
As a customer, I want to navigate to the checkout page to be able to buy my items. | Given I am a customer, when I click the checkout button, my shopping cart empties and I am able to buy my product. | Fail | JW; 3/21/2023; not implemented for this sprint |  |  | Pass | ax lc 4/4;
| Given I am a customer, when I don't have any products in my cart, the checkout button is greyed out. | Fail | JW; 3/21/2023; not implemented for this sprint |  |  | Pass | its not greyed out its just gone
| Given I am an admin, I should not have access to the checkout. | Fail | JW; 3/21/2023; not implemented for this sprint |  |  | Pass | ax lc 4/4;
As a customer, I want to be able to view a catalog of products so that I may see the products available for purchase. | Given some product exists, when I do not filter the results, that product will show up in the catalog list. | Pass | JW; 3/19/2023; all products show up in list when not filtered |  |  | Pass | ax lc 4/4;
| Given some product exists with certain criteria, when I filter the results with that criteria, this product will show up in the catalog list. | Pass | JW; 3/19/2023; product is filtered successfully when input is entered into field |  |  | Pass | ax lc 4/4;
| Given some product does not exist with certain criteria when I filter the results with that criteria, these products will not show up in the catalog list. | Pass | JW; 3/19/2023; products that do not meet criteria dont show up when input is entered into field |  |  | Pass | ax lc 4/4;
As a customer, I want to be able to sign up for an account that I can log back into at a later date. | Given I want to create an account, when I designate a username for myself, then I will be given a customer account with that username | Pass | JW; 3/19/2023; account created successfully with name |  |  | Pass | ax lc 4/4;
| Given I am logged in, I will not be able to see the create account page. | Pass | JW; 3/20/2023; Redirects to home page if logged in |  |  | Pass | ax lc 4/4;
| Given I try to create an account with a username already in use, then I will receive an error and be asked to try another username | Pass | JW; 3/19/2023; Displays proper error message |  |  | Pass | ax lc 4/4;
As a customer, I want there to be a navigation bar so that I can easily navigate the website. | Given there is a home icon, when I click on it, the site navigates to the landing page. | Fail | JW; 3/21/2023; not implemented for this sprint | Fail |  | Pass | ax lc 4/4;
| Given there is a cart icon, when I click on it, my shopping cart appears. | Fail | JW; 3/21/2023; not implemented for this sprint | Pass | JT GT; 04/04 | Pass | ax lc 4/4;
| Given there is an account icon, when I click on it, I am shown my account details. | Fail | JW; 3/21/2023; not implemented for this sprint | Fail | JT GT; 04/04 | Fail | ax lc 4/4;the buttons dont work
| Given there is a catalog icon, when I click on it, I am shown the catalog. | Fail | JW; 3/21/2023; not implemented for this sprint | Pass | JT GT; 04/04 | Pass | ax lc 4/4;
As a Administrator I want to manage the products in my inventory so that I can add, alter, and remove products for my customers to purchase | Given I am an admin when I open my dashboard then I can see my full inventory | Pass | AC; 3/20/23; when there is no inventory, list is empty, once I begin to create products they show up in the list | Pass | JT GT; 04/04 | Pass | ax lc 4/4;
| Given I am an admin when I add a item to my dashboard, it will be added to my inventory | Pass | AC; 3/20/23; Able to add products using the dashboard and they show up in inventory | Pass | JT GT; 04/04 | Fail | ax lc 4/4;its added to the catalog but its not added to the homepage
| Given I am an admin, when I alter a value in my inventory, it will be reflected in my stored inventory | Pass | AC; 3/20/23; Proucts are updated in inventory when changed on dashboard | Pass | JT GT; 04/04 | Fail | ax lc 4/4;changing weight doesnt work, it doubles and then adds the weight, updating price also doubles the weight
| Given I am an admin, when I click a button, then I will be able to remove the item from my inventory. | Pass | AC; 3/20/23; Removed items no longer appear in inventory | Pass | JT GT; 04/04 | Pass | ax lc 4/4;
As a customer, I want to be able to add products to my shopping cart so that I can proceed to checkout. | Given an item exists, when I try to add it to my shopping cart, a copy of that product is added to my shopping cart and I receive a 200 OK. | Pass | JW; 3/20/23; Items may be added via shopping cart page | Pass | AC 4/4/23 Items, weight, and prices are correctly added to cart | Pass | ax lc 4/4;
| Given an item doesn't exist, when I try to add it to my shopping cart, it does not add and I receive a 404 ERROR. | Pass | JW; 3/20/23; Attempting to add via backend results in 404 | Pass | AC 4/4/23 When I try to add inventory that does not exist than a warning comes up and nothing is added | Pass | ax lc 4/4; we can't test this
| Given an item exists, when I try to remove it from my shopping cart, a copy of that product is removed from my shopping cart and I receive a 200 OK. | Pass | JW; 3/20/23; Removing works from shopping cart page | Pass | AC 4/4/23 Items are removed correctly from cart | Pass | ax lc 4/4;
| Given an item doesn't exist, when I try to remove it from my shopping cart, it does not remove and I receive a 404 ERROR. | Pass | JW; 3/20/23; Attempting to remove nonexistent item results in 404 in backend | Pass | AC 4/4/23 if there is nothing in the cart than the remove option is not available | Pass | ax lc 4/4;
As a customer I want to be able to checkout with my shopping cart so that I can purchase my items | Given I have items in my shopping cart that are in stock when I checkout, then I purchase the items, and the inventory is updated and I get a 200 OK | Fail | JW; 3/21/2023; not implemented for this sprint | Pass | AC 4/4/23 Changes to inventory now happen when items are added to cart, but the other information is updated and works | Pass | ax lc 4/4;
| Given I have no items in my shopping cart when I checkout I get a 400 BAD REQUEST. | Fail | JW; 3/21/2023; not implemented for this sprint | Pass | AC 4/4/23 No ability to checkout if there is nothing in the cart, handled by front and back end | Pass | ax lc 4/4; cant test this
| Given I have items in my shopping cart that are not in stock when I check out, then I receive a 409 CONFLICT. | Fail | JW; 3/21/2023; not implemented for this sprint | Pass | AC 4/4/23 Now that inventory is updated when items are added to cart, this is no longer an issue | Pass | ax lc 4/4; can't test this
As a User I want to be able to login and stay logged in so that I don’t have to keep logging in when I navigate to each page | Given I am a user, when I am not logged in, then I should be sent to the home page | Pass | JW: 3/20/23 : redirected to home page from main url when not logged in | Pass | JT GT; 04/04 | Pass | ax lc 4/4;
| Given I am logged in when I naviagate between pages, then I should stay logged in | Pass | JW: 3/20/23; login is saved when switching pages | Pass | JT GT; 04/04 | Pass | ax lc 4/4;
| Given I am logged in as a customer, when I attempt to naviagate to admin only pages, then I should be redirected back to the landing page | Pass | JW: 3/20/23; redirects if customer on admin only page | Pass | JT GT; 04/04 | Pass | ax lc 4/4;
| Given I am logged in as a admin, when I attempt to navigate to customer only pages, then I should be redirected back to the landing page | Pass | JW: 3/20/23; redirects if admin on customer only page | Pass | JT GT; 04/04 | Pass | ax lc 4/4;
As a Developer I want more code coverage so that my updates are more robust | GIVEN I run a code coverage report WHEN all unit tests pass THEN I should reach at least 90% average code coverage on the backend API | Pass | JW: 3/21/23; passes w/ 93%
As an Customer, I want to view product images, so that I know what the product looks like. | Given a product has an image when I go to the product page I can see the image for the product |  |  | Fail | JT GT;04/04; no images | Fail | ax lc 4/4; there are no images
| Given there are some products in the inventory, when I visit the catalog, I can see the images of the products |  |  | Fail | JT GT;04/04; no images | Fail | ax lc 4/4; there are no images
| Given there are some products in the inventory, when I visit the home page, I can see the images of the featured products |  |  | Fail | JT GT;04/04; no images | Fail | ax lc 4/4; there are no images
As a developer I want to store customer credit card information in the customer class so that I can access each customer’s credit cards for ease of use | Given a customer has an account, when they add a credit card to their account, then it should be stored for future use |  |  | Fail | JT GT;04/04;No account info is displayed | Fail | ax lc 4/4 cant edit account
| Given a customer is trying to checkout their items, when they check out then they should have access to up to three of their previously used cards |  |  | Fail | JT GT;04/04;No credit card | Fail | ax lc 4/4; there are no account
As a user I want to be able to login using my password so that my account is more secure | Given my account has a password, when I login to my account using the password then I am logged into my account |  |  | Pass | JT GT; 04/04 | Pass | ax lc 4/4;
As a user I want to have a password associated with my user so that I can have a more secure account | Given I am a new user, when I am creating my account, I will provide a password for my account. |  |  | Pass | JT GT; 04/04 | Pass | ax lc 4/4;
As a user I want there to be an account page so that I can edit my credit cards and password | Given I am logged in When I visit the account page I am presented with the credit card and password components |  |  | Fail | JT GT;04/04;No credit card | Fail | ax lc 4/4; cant access account page
| Given I am not logged in When I visit the account page then I am redirected to the login page |  |  | Pass | JT GT; 04/04 | Fail | ax lc 4/4; cant access account page
As a user I want to be able to reset my password so that when I forget my password I can regain access to my account. | Given I have forgotten my password, when I reset my password, I will regain access to my account. |  |  | Fail | JT GT;04/04;No reset pw | Fail | ax lc 4/4; doesnt exist
As a customer I want to be able to add my cards to my account and choose which to use at checkout so that I can make purchases with my credit card | Given I am logged in When I visit the account page I am presented with the credit card and password components |  |  | Fail | JT GT;04/04;Naw | Fail | ax lc 4/4; no account page
| Given I am not logged in When I visit the account page then I am redirected to the login page |  |  | Fail | JT GT;04/04;No account page | Fail | ax lc 4/4; no account page
As a customer, I want the website to be aesthetically pleasing so I will enjoy using the site more. | Given I am a customer viewing the site then the site should have a uniform design |  |  | Pass | AC 4/4/23 Looks great. All site is uniform, requires fixes on individual css templates for cosmetic purposes | Pass | ax lc 4/4; boxes should be the same size
As a customer I want to be able to add my cards to my account and choose which to use at checkout so that I can make purchases with my credit card | GIVEN I am logged in WHEN I visit the account page THEN I am able to add and remove credit cards to my account |  |  | Fail | JT GT;04/04;No credit card | Fail | ax lc 4/4; cnt access account pagee
| GIVEN I have credit cards saved on my account WHEN I try to checkout THEN I am able to choose which credit card to use when I checkout |  |  | Fail | JT GT;04/04;No credit card | Fail | ax lc 4/4; cnt access account pagee